## Sheet1
BITS AUTOMATION ESTIMATION PLAN
S.No | User Role | Screens | Functionalities | Hrs | Start Date | End Date | Resource | Status
1 |  | Page Object Model Automation Framework Setup |  | 7 | 24/06/2021 | 24/06/2021 | Lokesh
9 | Admin | Reports | Allotted Station Student Faculty List | 16 | 29/09/2021 | 05/10/2021 | Rajeev | Yet to Start
|  |  | Allotted Station Details |  |  |  |  | Yet to Start
|  |  | Preferences Allotted Station |  |  |  |  | Yet to Start
|  |  | Problem Bank Details |  |  |  |  | Yet to Start
|  |  | Active Station |  |  |  |  | Yet to Start
|  |  | All Station Contact List |  |  |  |  | Yet to Start
|  |  | Allotted Faculty List |  |  |  |  | Yet to Start
|  |  | Student Course List |  |  |  |  | Yet to Start
|  |  | Student Bio Data |  |  |  |  | Yet to Start
|  |  | Station Faculty |  |  |  |  | Yet to Start
10 |  | Dashboard | Dashboard | 12 | 5/10/2021 | 08/10/2021 | Rajeev | In Progress
11 | Planning | Semester Allotment | Search List Validation | 10 | 07/09/2021 | 08/09/2021 | Sagunthala | Yet to Start
|  |  | Search by Student Name |  |  |  |  | Yet to Start
|  |  | Search by Campus ID |  |  |  |  | Yet to Start
|  |  | Sorting Grid |  |  |  |  | Yet to Start
|  |  | Show More/Less |  |  |  |  | Yet to Start
12 |  |  | Counts(Preferred, not filled) |  |  |  |  | Yet to Start
|  | Problem Bank List | Search List Validation | 8 | 08/09/2021 | 09/09/2021 | Sagunthala | Yet to Start
|  |  | Search by Station Name |  |  |  |  | Yet to Start
|  |  | Search by Station City |  |  |  |  | Yet to Start
|  |  | Search by Business Domain |  |  |  |  | Yet to Start
|  |  | Sorting Grid |  |  |  |  | Yet to Start
|  |  | Show More/Less |  |  |  |  | Yet to Start
13 |  | Problem Bank --> Add Problem | Add General Info | 14 | 09/09/2021 | 15/09/2021 | Sagunthala | Yet to Start
|  |  | Add Discipline --> Basic Information |  |  |  |  | Yet to Start
|  |  | Add Discipline --> Discipline details |  |  |  |  | Yet to Start
|  |  | Add Discipline --> Course details |  |  |  |  | Yet to Start
|  |  | Add Discipline --> Dual Degree details |  |  |  |  | Yet to Start
|  |  | Add Discipline --> Constraints |  |  |  |  | Yet to Start
|  |  | Reset Discipline |  |  |  |  | Yet to Start
|  |  | Expand and Collapse Discipline |  |  |  |  | Yet to Start
|  |  | Add Skill Set & Subject Area |  |  |  |  | Yet to Start
|  |  | Skill Set --> Add New Skill |  |  |  |  | Yet to Start
|  |  | Skill Set --> Add New Domain |  |  |  |  | Yet to Start
|  |  | Skill Set --> Edit Skill |  |  |  |  | Yet to Start
|  |  | Skill Set --> Edit Domain |  |  |  |  | Yet to Start
|  |  | Add Electives |  |  |  |  | Yet to Start
|  |  | Add Electives Course |  |  |  |  | Yet to Start
|  |  | Delete Electives Course |  |  |  |  | Yet to Start
|  |  | Add Facility |  |  |  |  | Yet to Start
|  |  | Expand and Collapse Functionality |  |  |  |  | Yet to Start
|  |  | Add Facility --> Stipend |  |  |  |  | Yet to Start
|  |  | Add Facility --> Office timing |  |  |  |  | Yet to Start
|  |  | Add Facility --> Accommodation |  |  |  |  | Yet to Start
|  |  | Add Facility --> Others |  |  |  |  | Yet to Start
14 |  | Problem Bank --> Edit Problem -> Project List | Search List Validation | 8 | 15/09/2021 | 16/09/2021 | Sagunthala | Yet to Start
|  |  | Search by Project Title |  |  |  |  | Yet to Start
|  |  | Sorting Grid |  |  |  |  | Yet to Start
15 |  | Problem Bank --> Edit Problem -> Add Project | Add General Info | 10 | 16/09/2021 | 17/09/2021 | Sagunthala | Yet to Start
|  |  | Add Discipline --> Basic Information |  |  |  |  | Yet to Start
|  |  | Add Discipline --> Discipline details |  |  |  |  | Yet to Start
|  |  | Add Discipline --> Course details |  |  |  |  | Yet to Start
|  |  | Add Discipline --> Dual Degree details |  |  |  |  | Yet to Start
|  |  | Add Discipline --> Constraints |  |  |  |  | Yet to Start
|  |  | Reset Discipline |  |  |  |  | Yet to Start
|  |  | Expand and Collapse Discipline |  |  |  |  | Yet to Start
|  |  | Add Skill Set & Subject Area |  |  |  |  | Yet to Start
|  |  | Skill Set --> Add New Skill |  |  |  |  | Yet to Start
|  |  | Skill Set --> Add New Domain |  |  |  |  | Yet to Start
|  |  | Skill Set --> Edit Skill |  |  |  |  | Yet to Start
|  |  | Skill Set --> Edit Domain |  |  |  |  | Yet to Start
|  |  | Add Electives |  |  |  |  | Yet to Start
|  |  | Add Electives Course |  |  |  |  | Yet to Start
|  |  | Delete Electives Course |  |  |  |  | Yet to Start
|  |  | Add Facility |  |  |  |  | Yet to Start
|  |  | Expand and Collapse Functionality |  |  |  |  | Yet to Start
|  |  | Add Facility --> Stipend |  |  |  |  | Yet to Start
|  |  | Add Facility --> Office timing |  |  |  |  | Yet to Start
|  |  | Add Facility --> Accomodation |  |  |  |  | Yet to Start
|  |  | Add Facility --> Others |  |  |  |  | Yet to Start
16 |  | Problem Bank --> Edit Problem -> Edit Project | Edit General Info | 12 | 20/09/2021 | 21/09/2021 | Sagunthala | Yet to Start
|  |  | Edit Discipline --> Basic Information |  |  |  |  | Yet to Start
|  |  | Edit Discipline --> Discipline details |  |  |  |  | Yet to Start
|  |  | Edit Discipline --> Course details |  |  |  |  | Yet to Start
|  |  | Edit Discipline --> Dual Degree details |  |  |  |  | Yet to Start
|  |  | Edit Discipline --> Constraints |  |  |  |  | Yet to Start
|  |  | Reset Discipline |  |  |  |  | Yet to Start
|  |  | Expand and Collapse Discipline |  |  |  |  | Yet to Start
|  |  | Edit Skill Set & Subject Area |  |  |  |  | Yet to Start
|  |  | Skill Set --> Edit New Skill |  |  |  |  | Yet to Start
|  |  | Skill Set --> Edit New Domain |  |  |  |  | Yet to Start
|  |  | Skill Set --> Edit Skill |  |  |  |  | Yet to Start
|  |  | Skill Set --> Edit Domain |  |  |  |  | Yet to Start
|  |  | Edit Electives |  |  |  |  | Yet to Start
|  |  | Edit Electives Course |  |  |  |  | Yet to Start
|  |  | Delete Electives Course |  |  |  |  | Yet to Start
|  |  | Add Facility |  |  |  |  | Yet to Start
|  |  | Expand and Collapse Functionality |  |  |  |  | Yet to Start
|  |  | Edit Facility --> Stipend |  |  |  |  | Yet to Start
|  |  | Edit Facility --> Office timing |  |  |  |  | Yet to Start
|  |  | Edit Facility --> Accomodation |  |  |  |  | Yet to Start
|  |  | Edit Facility --> Others |  |  |  |  | Yet to Start
17 |  | Manage Station List | Search List Validation | 8 | 21/09/2021 | 22/09/2021 | Sagunthala | Yet to Start
|  |  | Search by Station Name |  |  |  |  | Yet to Start
|  |  | Search by Business Domain |  |  |  |  | Yet to Start
|  |  | Search by Parent Company |  |  |  |  | Yet to Start
|  |  | Sorting Grid |  |  |  |  | Yet to Start
|  |  | Action by Delete |  |  |  |  | Yet to Start
18 |  | Manage Station Detail | Mandatory Validation | 8 | 22/09/2021 | 23/09/2021 | Sagunthala | Yet to Start
|  |  | Add and Cancel Station |  |  |  |  | Yet to Start
|  |  | Edit Station |  |  |  |  | Yet to Start
|  |  | Expand and Collapse Functionality |  |  |  |  | Yet to Start
19 |  | Station Allotment | Station Allotment --> Station Preference | 8 | 23/09/2021 | 27/09/2021 | Sagunthala | Yet to Start
|  |  | Station Allotment --> Student Preference |  |  |  |  | Yet to Start
20 |  | Faculty Allotment | Faculty Allotment --> View Group Leader Allotment | 12 | 27/09/2021 | 30/09/2021 | Sagunthala | Yet to Start
|  |  | Faculty Allotment --> Station/Faculty wise Allotment |  |  |  |  | Yet to Start
|  |  | Faculty Allotment --> View Faculty Allotment |  |  |  |  | Yet to Start
21 |  | Post Allotment | Post Allotment --> Station Wise | 12 | 01/10/2021 | 06/10/2021 | Sagunthala | Yet to Start
|  |  | Post Allotment --> Faculty Wise |  |  |  |  | Yet to Start
|  |  | Post Allotment --> Student Wise |  |  |  |  | Yet to Start
22 |  | Announcement | Announcement | 8 | 07/10/2021 | 08/10/2021 | Sagunthala | Yet to Start
23 |  | Reports | Allotted Station Student Faculty List | 12 | 11/10/2021 | 14/10/2021 | Sagunthala | Yet to Start
|  |  | Allotted Station Details |  |  |  |  | Yet to Start
|  |  | Preferences Allotted Station |  |  |  |  | Yet to Start
|  |  | Problem Bank Details |  |  |  |  | Yet to Start
|  |  | Active Station |  |  |  |  | Yet to Start
|  |  | All Station Contact List |  |  |  |  | Yet to Start
|  |  | Allotted Faculty List |  |  |  |  | Yet to Start
|  |  | Student Course List |  |  |  |  | Yet to Start
|  |  | Student Bio Data |  |  |  |  | Yet to Start
24 |  | Dashboard | Dashboard | 3 | 14/10/2021 | 15/10/2021 | Sagunthala | Yet to Start
34 | Student | Station Allotment | Add/Edit Preference | 8 | 11/10/2021 | 12/10/2021 | Rajeev | Yet to Start
|  |  | Preference details Screen |  |  |  |  | Yet to Start
|  |  | Grievance |  |  |  |  | Yet to Start
35 |  | Reports | Active Station | 5 | 12/10/2021 | 13/10/2021 | Rajeev | Yet to Start
|  |  | All Station Contact List |  |  |  |  | Yet to Start
|  |  | Student Course List |  |  |  |  | Yet to Start
|  |  | Student Bio Data |  |  |  |  | Yet to Start
|  | Dashboard | Stepper Bar(Metro) | 8 | 13/10/2021 | 15/10/2021 | Rajeev | Yet to Start
|  |  | General Informations |  |  |  |  | Yet to Start
36 |  |  | Bio Data |  |  |  |  | Yet to Start
37 |  |  | Station Preference |  |  |  |  | Yet to Start
46 | Faculty | Post Allotment | Post Allotment --> Station Wise | 12 | 18/10/2021 | 21/10/2021 | Rajeev | Yet to Start
|  |  | Post Allotment --> Faculty Wise |  |  |  |  | Yet to Start
|  |  | Post Allotment --> Student Wise |  |  |  |  | Yet to Start
47 |  | Faculty Allotment | Faculty Allotment --> Group Leader Allotment | 12 | 22/10/2021 | 27/10/2021 | Rajeev | Yet to Start
|  |  | Faculty Allotment --> Station/Faculty wise Allotment |  |  |  |  | Yet to Start
|  |  | Faculty Allotment --> View FacultyAllotment |  |  |  |  | Yet to Start
48 |  | Reports | Allotted Station Student Faculty List | 5 | 27/10/2021 | 28/10/2021 | Rajeev | Yet to Start
|  |  | Allotted Station Details |  |  |  |  | Yet to Start
|  |  | Preferences Allotted Station |  |  |  |  | Yet to Start
|  |  | Problem Bank Details |  |  |  |  | Yet to Start
|  |  | Active Station |  |  |  |  | Yet to Start
|  |  | All Station Contact List |  |  |  |  | Yet to Start
|  |  | Allotted Faculty List |  |  |  |  | Yet to Start
|  |  | Student Course List |  |  |  |  | Yet to Start
|  |  | Student Bio Data |  |  |  |  | Yet to Start
|  |  | Station Faculty |  |  |  |  | Yet to Start
49 |  | Dashboard | Allotment Details | 8 | 28/10/2021 | 29/10/2021 | Rajeev | In Progress
50 | Allotment | Semester Allotment --> All Alloted Student List | Search Validation | 9 | 18/10/2021 | 20/10/2021 | Sagunthala | In Progress
|  |  | Search by Campus |  |  |  |  | In Progress
|  |  | list validation |  |  |  |  | In Progress
|  |  | Show More/Less |  |  |  |  | In Progress
51 |  | Semester Allotment --> Student Semester Allotment | Search Validation | 8 | 20/10/2021 | 21/10/2021 | Sagunthala | In Progress
|  |  | Search by Student Name |  |  |  |  | In Progress
|  |  | Search by Campus ID |  |  |  |  | In Progress
|  |  | Sorting Grid |  |  |  |  | In Progress
|  |  | Show More/Less |  |  |  |  | In Progress
|  |  | Grievance |  |  |  |  | In Progress
|  |  | Update Allotment |  |  |  |  | In Progress
|  |  | Allot |  |  |  |  | In Progress
|  |  | Publish |  |  |  |  | In Progress
52 |  | Station --> Station List | Search List Validation | 2 | 22/10/2021 | 22/10/2021 | Sagunthala | Yet to Start
|  |  | Search by Station Name |  |  |  |  | Yet to Start
|  |  | Search by Business Domain |  |  |  |  | Yet to Start
|  |  | Search by Parent Company |  |  |  |  | Yet to Start
|  |  | Sorting Grid |  |  |  |  | Yet to Start
|  |  | Action by Delete |  |  |  |  | Yet to Start
53 |  | Station --> Add Station | Mandatory Validation | 3 | 22/10/2021 | 22/10/2021 | Sagunthala | Yet to Start
|  |  | Add and Cancel Station |  |  |  |  | Yet to Start
|  |  | Edit Station |  |  |  |  | Yet to Start
|  |  | Expand and Collapse Functionality |  |  |  |  | Yet to Start
54 |  | Station Allotment | Station Allotment --> Announce Station | 13 | 25/10/2021 | 28/10/2021 | Sagunthala | Yet to Start
|  |  | Station Allotment --> Convert Station |  |  |  |  | Yet to Start
|  |  | Station Allotment --> Converted Station List |  |  |  |  | Yet to Start
|  |  | Station Allotment --> Allotment |  |  |  |  | Yet to Start
55 |  | Post Allotment | Post Allotment --> Station Wise | 13 | 28/10/2021 | 2/11/2021 | Sagunthala | Yet to Start
|  |  | Post Allotment --> Faculty Wise |  |  |  |  | Yet to Start
|  |  | Post Allotment --> Student Wise |  |  |  |  | Yet to Start
|  | Dashboard | Dashboard | 5 | 03/11/2021 | 04/11/2021 | Sagunthala | Yet to Start
57 | Dean | Dashboard | Dashboard | 8 |  |  | Pushpaleela | Yet to Start
58 |  | Reports | Allotted Station Student Faculty List | 12 |  |  | Pushpaleela | Yet to Start
|  |  | Allotted Station Details |  |  |  |  | Yet to Start
|  |  | Preferences Allotted Station |  |  |  |  | Yet to Start
|  |  | Problem Bank Details |  |  |  |  | Yet to Start
|  |  | Active Station |  |  |  |  | Yet to Start
|  |  | All Station Contact List |  |  |  |  | Yet to Start
|  |  | Allotted Faculty List |  |  |  |  | Yet to Start
|  |  | Student Course List |  |  |  |  | Yet to Start
|  |  | Student Bio Data |  |  |  |  | Yet to Start
|  |  | Station Facilities |  |  |  |  | Yet to Start
59 | Instruction Cell | Dashboard | Dashboard | 5 |  |  | Pushpaleela | Yet to Start
60 |  | Suggest Station List | Search List Validation | 8 |  |  | Pushpaleela | Yet to Start
|  |  | Search by Station Name |  |  |  |  | Yet to Start
|  |  | Search by Business Domain |  |  |  |  | Yet to Start
|  |  | Search by Parent Company |  |  |  |  | Yet to Start
|  |  | Sorting Grid |  |  |  |  | Yet to Start
|  |  | Action by Delete |  |  |  |  | Yet to Start
61 |  | Suggest Station Detail | Mandatory Validation | 8 |  |  | Pushpaleela | Yet to Start
|  |  | Add and Cancel Station |  |  |  |  | Yet to Start
|  |  | Edit Station |  |  |  |  | Yet to Start
|  |  | Expand and Collapse Functionality |  |  |  |  | Yet to Start
62 |  | Problem Bank List | Search List Validation | 8 |  |  | Pushpaleela | Yet to Start
|  |  | Search by Station Name |  |  |  |  | Yet to Start
|  |  | Search by Station City |  |  |  |  | Yet to Start
|  |  | Search by Business Domain |  |  |  |  | Yet to Start
|  |  | Sorting Grid |  |  |  |  | Yet to Start
|  |  | Show More/Less |  |  |  |  | Yet to Start
64 |  | Problem Bank --> Add Problem | Add General Info | 14 |  |  | Pushpaleela | Yet to Start
|  |  | Add Discipline --> Basic Information |  |  |  |  | Yet to Start
|  |  | Add Discipline --> Discipline details |  |  |  |  | Yet to Start
|  |  | Add Discipline --> Course details |  |  |  |  | Yet to Start
|  |  | Add Discipline --> Dual Degree details |  |  |  |  | Yet to Start
|  |  | Add Discipline --> Constraints |  |  |  |  | Yet to Start
|  |  | Reset Discipline |  |  |  |  | Yet to Start
|  |  | Expand and Collapse Discipline |  |  |  |  | Yet to Start
|  |  | Add Skill Set & Subject Area |  |  |  |  | Yet to Start
|  |  | Skill Set --> Add New Skill |  |  |  |  | Yet to Start
|  |  | Skill Set --> Add New Domain |  |  |  |  | Yet to Start
|  |  | Skill Set --> Edit Skill |  |  |  |  | Yet to Start
|  |  | Skill Set --> Edit Domain |  |  |  |  | Yet to Start
|  |  | Add Electives |  |  |  |  | Yet to Start
|  |  | Add Electives Course |  |  |  |  | Yet to Start
|  |  | Delete Electives Course |  |  |  |  | Yet to Start
|  |  | Add Facility |  |  |  |  | Yet to Start
|  |  | Expand and Collapse Functionality |  |  |  |  | Yet to Start
|  |  | Add Facility --> Stipend |  |  |  |  | Yet to Start
|  |  | Add Facility --> Office timing |  |  |  |  | Yet to Start
|  |  | Add Facility --> Accommodation |  |  |  |  | Yet to Start
|  |  | Add Facility --> Others |  |  |  |  | Yet to Start
65 |  | Problem Bank --> Edit Problem -> Project List | Search List Validation | 8 |  |  | Pushpaleela | Yet to Start
|  |  | Search by Project Title |  |  |  |  | Yet to Start
|  |  | Sorting Grid |  |  |  |  | Yet to Start
66 |  | Problem Bank --> Edit Problem -> Add Project | Add General Info | 10 |  |  | Pushpaleela | Yet to Start
|  |  | Add Discipline --> Basic Information |  |  |  |  | Yet to Start
|  |  | Add Discipline --> Discipline details |  |  |  |  | Yet to Start
|  |  | Add Discipline --> Course details |  |  |  |  | Yet to Start
|  |  | Add Discipline --> Dual Degree details |  |  |  |  | Yet to Start
|  |  | Add Discipline --> Constraints |  |  |  |  | Yet to Start
|  |  | Reset Discipline |  |  |  |  | Yet to Start
|  |  | Expand and Collapse Discipline |  |  |  |  | Yet to Start
|  |  | Add Skill Set & Subject Area |  |  |  |  | Yet to Start
|  |  | Skill Set --> Add New Skill |  |  |  |  | Yet to Start
|  |  | Skill Set --> Add New Domain |  |  |  |  | Yet to Start
|  |  | Skill Set --> Edit Skill |  |  |  |  | Yet to Start
|  |  | Skill Set --> Edit Domain |  |  |  |  | Yet to Start
|  |  | Add Electives |  |  |  |  | Yet to Start
|  |  | Add Electives Course |  |  |  |  | Yet to Start
|  |  | Delete Electives Course |  |  |  |  | Yet to Start
|  |  | Add Facility |  |  |  |  | Yet to Start
|  |  | Expand and Collapse Functionality |  |  |  |  | Yet to Start
|  |  | Add Facility --> Stipend |  |  |  |  | Yet to Start
|  |  | Add Facility --> Office timing |  |  |  |  | Yet to Start
|  |  | Add Facility --> Accomodation |  |  |  |  | Yet to Start
|  |  | Add Facility --> Others |  |  |  |  | Yet to Start
67 |  | Problem Bank --> Edit Problem -> Edit Project | Edit General Info | 12 |  |  | Pushpaleela | Yet to Start
|  |  | Edit Discipline --> Basic Information |  |  |  |  | Yet to Start
|  |  | Edit Discipline --> Discipline details |  |  |  |  | Yet to Start
|  |  | Edit Discipline --> Course details |  |  |  |  | Yet to Start
|  |  | Edit Discipline --> Dual Degree details |  |  |  |  | Yet to Start
|  |  | Edit Discipline --> Constraints |  |  |  |  | Yet to Start
|  |  | Reset Discipline |  |  |  |  | Yet to Start
|  |  | Expand and Collapse Discipline |  |  |  |  | Yet to Start
|  |  | Edit Skill Set & Subject Area |  |  |  |  | Yet to Start
|  |  | Skill Set --> Edit New Skill |  |  |  |  | Yet to Start
|  |  | Skill Set --> Edit New Domain |  |  |  |  | Yet to Start
|  |  | Skill Set --> Edit Skill |  |  |  |  | Yet to Start
|  |  | Skill Set --> Edit Domain |  |  |  |  | Yet to Start
|  |  | Edit Electives |  |  |  |  | Yet to Start
|  |  | Edit Electives Course |  |  |  |  | Yet to Start
|  |  | Delete Electives Course |  |  |  |  | Yet to Start
|  |  | Add Facility |  |  |  |  | Yet to Start
|  |  | Expand and Collapse Functionality |  |  |  |  | Yet to Start
|  |  | Edit Facility --> Stipend |  |  |  |  | Yet to Start
|  |  | Edit Facility --> Office timing |  |  |  |  | Yet to Start
|  |  | Edit Facility --> Accomodation |  |  |  |  | Yet to Start
|  |  | Edit Facility --> Others |  |  |  |  | Yet to Start
68 |  | Post Allotment | Post Allotment --> Station Wise | 5 |  |  | Pushpaleela | Yet to Start
|  |  | Post Allotment --> Faculty Wise |  |  |  |  | Yet to Start
|  |  | Post Allotment --> Student Wise |  |  |  |  | Yet to Start
69 |  | Faculty Allotment | Faculty Allotment --> View Group Leader Allotment | 5 |  |  | Pushpaleela | Yet to Start
|  |  | Faculty Allotment --> Station/Faculty wise Allotment |  |  |  |  | Yet to Start
|  |  | Faculty Allotment --> View Faculty Allotment |  |  |  |  | Yet to Start
70 |  | Reports | Allotted Station Student Faculty List | 12 |  |  | Pushpaleela | Yet to Start
|  |  | Allotted Station Details |  |  |  |  | Yet to Start
|  |  | Preferences Allotted Station |  |  |  |  | Yet to Start
|  |  | Problem Bank Details |  |  |  |  | Yet to Start
|  |  | Active Station |  |  |  |  | Yet to Start
|  |  | All Station Contact List |  |  |  |  | Yet to Start
|  |  | Allotted Faculty List |  |  |  |  | Yet to Start
|  |  | Student Course List |  |  |  |  | Yet to Start
|  |  | Student Bio Data |  |  |  |  | Yet to Start
|  |  | Station Facilities |  |  |  |  | Yet to Start
| Total Hours |  |  | 394